## Format
MES's Institute of Management and Career Courses (IMCC)
Mini Project FY MCA- SEM I
Academic Year 2020-21
Name of Project:
Project Start |  | 2021-02-18 | Module alloted
Other Members
Team Member-1 |  | Shubham Sakpal :2012118 | Front-end, Validation, Diagram, Testing
Team Member-2 |  | Chinmay Parulekar :2012100 | Requirements, Front-end, Validation, Dumantation, Diagrams, Testing
Level | WBS | Task Description | Learnings | Start Date | End Date | Remark | Approved By & Date
1 | 1 | Project Topic decision
2 | 1.1 | Meeting with team members | The first meeting with team members held regarding searching of the project topics. | 2021-12-20 | 2021-12-24
2 | 1.2 | Topic discussion | Each team member came up with few different topics on which we had discussion atlast we finalize few of them. | 2021-12-25 | 2021-12-26
3 | 1.2.1 | Topic finalisation | All four of us had a different point of view. Therefore we decided to discuss in detail on all topics & finally we decided the topic which had broader scope and something which is new in learning purpose. | 2021-12-28 | 2022-01-01
3 | 1.3 | Scope coverage | Scope of project is broad in nature as it will contain 3 modules having many sub modules which help to maintain all student and teachers data. | 2022-01-10 | 2022-01-14
4 | 1.3.1 | Scope approval | Scope of the project is approved by project guide. | 2022-01-15 | 2022-01-20
1 | 2 | Synopsis Submission
2 | 2.1 | Scope | This project contains a web application in which admin can add students and assign subjects to teachers. Teachers can mark attendance of students. The web app will provide feedback and leaves facility to student and teachers. There will be main three characters are Admin, Teacher and Student. Admin can give permission to leave applications. | 2022-01-24 | 2022-01-25
3 | 2.2 | Modules | Module & Module Division: 1. ADMIN:- 1.1 Class-Subject Creation 1.2 Assigning Students and Teachers 1.3 Subject Assigning 2. TEACHER:- 2.1 Manual attendance 2.2 Live Attendance Reports 2.3 Apply for Leave 3. STUDENT:- 3.1 Check attendance list 3.2 Give feedbacks 3.3 Apply for Leave | 2022-01-26 | 2022-01-27
3 | 2.3 | Technology Description | 1:Hardware Requirements:- Mobile: Android Phone and IOS phone: 2: Software Requirements:- Operating system: Android OS and Mac OS: Mobile phones having android operating system (eg. Samsung, Realme) or having ios operating system (eg. iphone) can easily install or operate this application. Windows OS Keyboard & mouse. | 2022-01-26 | 2022-01-27
1 | 3 | Submission – algorithm
2 | 3.1 | Discussion | Algorithm is set of instruction to perform specific task in the most efficient manner of the system | 2022-02-09 | 2022-02-10
3 | 3.2 | Representation | Algorithm representation shows flow of the logic such as entry, exit, task, input/output. | 2022-02-09 | 2022-02-10
1 | 4 | Database design/ Input design
2 | 4.1 | Discussion on Data Fields required | For each modules | 2022-02-11 | 2022-02-12
3 | 4.2 | Preparing List of fields | List of fields is prepared inorder to fulfill the complete requirement of the each modules. | 2022-02-13 | 2022-02-14
4 | 4.3 | Table design | Tables of the modules are designed according to the fields and are connected to each other according to required relationship. | 2022-02-15 | 2022-02-15
1 | 5 | Screen design
2 | 5.1 | Assigning screens to mambers | According to the allotment of modules to each members screens are assigned according to that specific module requirement. | 2022-02-16 | 2022-02-16
3 | 5.2 | Designing screen | Screens are designed in very user friendly manner with simplest Graphical User Interface (GUI) & will provide ease of use of system. | 2022-02-17 | 2022-02-22
1 | 6 | Validation
2 | 6.1 | Applying contraints on fields | Each and every field has minimum one or more constraints according to requirement of that particular field(s). | 2022-02-23 | 2022-02-24
3 | 6.2 | code against field validation | Coding of fields is done according to the constraints of fields. | 2022-02-25 | 2022-02-28
1 | 7 | Integration of screens/ modules
2 | 7.1 | Designing Menu Screen | The Dashboard screen design contains link to all modules present in system. | 2022-03-01 | 2022-03-09
3 | 7.2 | Call every screen from Menu | Every screen present in each module is callable from the menu. | 2022-03-10 | 2022-03-17
1 | 8 | Project Execution
2 | 8.1 | Debuging for error | As and when we are testing the system with different types of input we are debugging errors occurred during project execution. | 2022-03-18 | 2022-03-23
3 | 8.2 | Resolve errors | Resolving the different kinds of errors occurred during runtime. | 2022-03-24 | 2022-03-28
* WBS = Work Breakdown Structure